## Dashboard
Closeout Tracking Dashboard
| Foremost | 0 | 0
Refresh the sheet Before Use see below
Right click on any of the filter and select Refresh button
* For more filter please refer the guideline
(Click here) (you will see advanced filter from coloumn W to AI)
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Final
Closeout Matrix | [6 empty] | Tracking Log
S.NO | Division | Spec Number | Spec Name | Spec Sub Section | Document Type | Descriptions | Block/Building | Trade Partner | Comments | Submitted To DPR | Updated To Box Folder
1 | 01 - General Requirements | 01 50 00 | Temporary Facilities And Controls | 1.3/A/1 | Test-Reports | Temporary Utilities | DLR L236
2 | 01 - General Requirements | 01 73 29 | Cutting And Patching | 1.5/A | Warranty - Manufacturer | Standard Product Warranties | DLR L236
3 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/2 | As-Builts | 1. Project Record Drawings - 2 Sets Of Drawings 2. Blackline Print Drawings - 1 Set | DLR L236
4 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/4,6 | O&M Data | 1. Preventive Maintenance Instructions - 3 Bound Copies 2. Maintenance Contracts - 2 Copies | DLR L236
5 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/5 | Warranty - Manufacturer | Product Warranties And Bonds - 2 Copies | DLR L236
6 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/7 | Test-Reports | Record Of All Test Reports And Inspections - 4 Copies | DLR L236
7 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.7/A | O&M Data | 1. Fire Protection System. 2. Utilities And Plumbing Systems. 3. Heating, Ventilation And Air Conditioning System. 4. Electrical Systems. | DLR L236
8 | 01 - General Requirements | 01 78 36 | Warranties | 1.3 | Warranty - Manufacturer | Standard Product Warranties | DLR L236
9 | 01 - General Requirements | 01 78 36 | Warranties | 1.4 | Warranty - Sample/Special | Special Warranties | DLR L236
10 | 01 - General Requirements | 01 79 00 | Demonstration And Training | 1.3 | Owner Training | 1. General Overview Of Record Documents - Not Less Than 3 Hours 2. Fire Protection Systems And Equipment: Not Less Than 6 Hours 3. Fire Alarms Systems And Equipment: Not Less Than 8 Hours 4. Hvac Systems And Equipment: Not Less Than 32 Hours 5. Plumbing Systems And Equipment: Not Less Than 6 Hours 6. Electrical Systems And Equipment (Including Emergency Generator): Not Less Than 32 Hours 7. Audio-Visual Systems, Sound Systems And Similar Equipment: Not Less Than 4 Hours 8. Other Utility Connected Systems, Control Systems, Security Systems, And Similar Equipment: Not Less Than 8 Hours | DLR L236
11 | 03 - Concrete | 03 01 36 | Resurfacing And Patching Of Concrete Slabs | 1.4/A/2 | Test-Reports | Preliminary Design Mix Reports | DLR L236 | K&A Contracting
12 | 03 - Concrete | 03 30 00 | Cast-In-Place Concrete | 1.5 | Test-Reports | 1. Aggregates 2. Field Quality-Control Reports | DLR L236 | K&A Contracting
13 | 04 - Masonary | 04 20 00 | Unit Masonary | 1.4/A/3 | Test-Reports | 1. Mortar 2. Grout Mixes 3. Masonary Units | DLR L236 | TBD
14 | 05 - Metals | 05 12 00 | Structural Steel Framing | 1.6 | Test-Reports | 1. Mill Test Reports For Structural Steel 2. Bolts, Nuts, And Washers 3. Direct-Tension Indicators 4. Tension-Control, High-Strength Bolt-Nut-Washer Assemblies | DLR L236 | Hallmark
15 | 05 - Metals | 05 50 00 | Metal Fabrications | 1.5/B/1 | Other | Special Inspections | DLR L236 | Hallmark
16 | 07 - Thermal And Moisture Protections | 07 59 00 | Cutting And Patching Membrane Roofing | 1.4/B/1 | Test-Reports | Manufacturer’S Field Quality Control Reports Of Field Inspections | DLR L236 | American Automatic FP
17 | 07 - Thermal And Moisture Protections | 07 59 00 | Cutting And Patching Membrane Roofing | 1.4/B/2 | Warranty - Manufacturer | Manufacturer’S Warranties | DLR L236 | American Automatic FP
18 | 07 - Thermal And Moisture Protections | 07 59 00 | Cutting And Patching Membrane Roofing | 1.9/A | Warranty - Manufacturer | For Membrane Roofing - 20 Years | DLR L236 | American Automatic FP
19 | 07 - Thermal And Moisture Protection | 07 6200 | Sheet Metal Flashing And Trim | 1.7/A/1 | Warranty - Sample/Special | Exposed Panel Finish - 20 Years | DLR L236 | American Automatic FP
20 | 07 - Thermal And Moisture Protection | 07 72 00 | Roof Accessories | 1.8/A | Warranty - Manufacturer | Roof Accessories - 5 Years | DLR L236 | American Automatic FP
21 | 07 - Thermal And Moisture Protection | 07 84 00 | Firestopping | 1.5/A/4 | Test-Reports | Fire Stop Material | DLR L236 | American Automatic FP
22 | 07 - Thermal And Moisture Protection | 07 92 00 | Joint Sealents | 1.8/A | Warranty - Manufacturer | Installed Sealent And Accessories - 5 Years | DLR L236 | American Automatic FP
23 | 08 - Openings | 08 11 13 | Hollow Metal Doors And Frames | 1.5/B/1 | Warranty - Manufacturer | Hollow Metal And Door Frames | DLR L236 | Precision
24 | 08 - Openings | 08 70 00 | Hardware | 1.3/H | Keys | Submit 6 Copies Of Keying Schedule Indicating Door Numbers In Numerical Sequence, And Its Particular Keying | DLR L236 | Precision
25 | 08 - Openings | 08 70 00 | Hardware | 1.3/I/2 | O&M Data | 2 Maintenance Manuals At Accaptance Of Work | DLR L236 | Precision
26 | 08 - Openings | 08 70 00 | Hardware | 1.3/I/2/e | O&M Data | Manufacturer’S Maintenance Instruction And Maintenance Schedule | DLR L236 | Precision
27 | 08 - Openings | 08 70 00 | Hardware | 1.3/I/2/g | Other | Manufacturer Bitting List | DLR L236 | Precision
28 | 08 - Openings | 08 70 00 | Hardware | 1.7/A/1 | Warranty - Sample/Special | 1.Hinges - (Life Of Building) 2.Continuous Hinges - 10 Years 3.Door Closers - 10 Years 4.Door Closers With Electric Or Pneumatic Components - 2 Years 5.Exit Devices - 3 Years 6.Remainder Of Hardware - 1 Year | DLR L236 | Precision
29 | 08 - Openings | 08 70 00 | Hardware | 1.8/A/1 | Owner Training | Training For Proper Use, Servicing, Adjustment And Maintenance Of Door Hardware | DLR L236 | Precision
30 | 08 - Openings | 08 70 00 | Hardware | 1.8/B/1 | O&M Data | Approximately 6 Months After Acceptance Of Work, Arrange To Have Installer Of Hardware In Company With Representatives Of Lock, Exit Device And Closer Manufacturers Contact Owner And Make Arrangements For An Inspection Of Hardware. | DLR L236 | Precision
31 | 08 - Openings | 08 80 00 | Glazing | 1.9/B/1 | Warranty - Manufacturer | Laminated Glass - 4 Years | DLR L236 | Precision
32 | 08 - Openings | 08 91 00 | Louvers | 1.4/E | Test-Reports | Louvers Performance Criteria | DLR L236 | Precision
33 | 08 - Openings | 08 91 00 | Louvers | 1.6/B | Warranty - Manufacturer | Finish - 20 Years | DLR L236 | Precision
34 | 09 - Finishes | 09 51 00 | Acoustical Ceilings | 1.10/A | Warranty - Manufacturer | All Furnished Materials | DLR L236 | Capital City Flooring
35 | 09 - Finishes | 09 51 00 | Acoustical Ceilings | 1.11/A | Attic Stock | Extra Ceiling Panel And Suspension Components - 3 % Of Each Type Installed | DLR L236 | Capital City Flooring
36 | 09 - Finishes | 09 65 13 | Resilient Base And Accessories | 1.5/B/1 | Attic Stock | Resilient Base - 24 Linear Feet | DLR L236 | Capital City Flooring
37 | 09 - Finishes | 09 65 13 | Resilient Base And Accessories | 1.9/B | Warranty - Manufacturer | 1. Resilient Base - 1 Year 2. Adhesives - 1 Year | DLR L236 | Capital City Flooring
38 | 09 - Finishes | 09 69 00 | Access Flooring | 1.5/B/1 | O&M Data | Data Including Recommended Cleaning Methods, Cleaning Materials Stain Removal Methods | DLR L236 | Capital City Flooring
39 | 09 - Finishes | 09 69 00 | Access Flooring | 1.12/A | Warranty - Manufacturer | Access Flooring - 5 Years | DLR L236 | Capital City Flooring
40 | 09 - Finishes | 09 69 00 | Access Flooring | 1.13/A | Attic Stock | 1. Floor Panel (Floor Tile) 2. Perforated Floor Panels (General Stock) - One Perforated Tile Per Every 4 Kw Of Ups Power Plus An Additional 5 Percent Stock 3. System “Af-1” Floor Panels - Sufficient Stock To Back Fill 75 Percent Of Perforated Tiles For Initial Build Out Of First Pod 4. System “Af-5” Floor Panels - 10 Floor Panels Per Computer Room 5. System “Af-6” Floor Panels - 10 Floor Panels Per Computer And Idf Room 6. Stringers - 25 Spare Stringers For Each System Type 7. Pedestals - 25 Spare Pedestals For Each System Type 8. Panel Lifting Devices - One Panel Lifting Device Per Door And An Additional Quantity Of One Per Every 1,500 Square Feet Of Access Flooring | DLR L236 | Capitol Coatings
41 | 09 - Finishes | 09 91 00 | Painting | 1.4/B/1 | Mockups | Color Chips | DLR L236 | Capitol Coatings
42 | 09 - Finishes | 09 97 26 | Exterior Textured Coatings | 1.4/A/5 | Test-Reports | Compatibility And Adhesion Test Reports | DLR L236 | Capitol Coatings
43 | 09 - Finishes | 09 97 26 | Exterior Textured Coatings | 1.8/A | Warranty - Manufacturer | Exterior Textured Coating | DLR L236 | Capitol Coatings
44 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 1.7/A | Attic Stock | Provide Extra Material Under Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP
45 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 1.9/A | O&M Data | Provide Operating Instruction And Maintainence Data For Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP
46 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 1.10/A | Warranty - Manufacturer | Provide Warranty For Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP
47 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 3.3/C | Owner Training | Provide Owner Training For Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP
48 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 1.7/E | O&M Data | Submit Maintenance Instructions: Include Installation Instructions, Spare Parts Lists, Procedures, And Treatment Programs | DLR L236 | American Automatic FP
49 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 1.12/B/1 | Attic Stock | Sprinkler Cabinets - Minimum Of Six Spare Sprinklers Plus Sprinkler Wrench | DLR L236 | American Automatic FP
50 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 1.15 | Warranty - Manufacturer | For Sprinkler Systems | DLR L236 | American Automatic FP
51 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 3.15/A | Owner Training | Train Owner’S Maintenance Personnel To Adjust, Operate, And Maintain Specialty Valves | DLR L236 | American Automatic FP
52 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 1.7/A | Attic Stock | Provide Extra Material Under Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air
53 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 1.9/A | O&M Data | Provide Operating Instruction And Maintainence Data For Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air
54 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 1.10/A | Warranty - Manufacturer | Provide Warranty For Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air
55 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 3.3/C | Owner Training | Provide Owner Training For Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air
56 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.5/C | Test-Reports | Field Quality-Control Inspection And Test Reports | DLR L236 | Pro Air
57 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.5/D | Other | Record Drawings And Final Certification | DLR L236 | Pro Air
58 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.8/A | Warranty - Manufacturer | Standard Product | DLR L236 | Pro Air
59 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.8/B | Warranty - Installer | For Plumbing Systems - 1 Year | DLR L236 | Pro Air
60 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.9/A | Other | Project Record Drawings | DLR L236 | Pro Air
61 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 00 10 | General Mechanical Requirements | 1.7 | Attic Stock | Extra Materials | DLR L236 | Pro Air
62 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 00 10 | General Mechanical Requirements | 1.10/D | Warranty - Manufacturer | Guarantee Against All Defects In Materials And Workmanship For 1 Year | DLR L236 | Pro Air
63 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 00 10 | General Mechanical Requirements | 3.4/C | Test-Reports | 1. Submit All Test Reports 2. Submit Local Authority Final Sign Off Inspection Reports | DLR L236 | Pro Air
64 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 05 13 | Common Motor Requirements For HVAC Equipment | 1.7 | Attic Stock | For Motor Requirements For Hvac Equipment | DLR L236 | Pro Air
65 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 05 13 | Common Motor Requirements For HVAC Equipment | 1.9 | O&M Data | For Motor Requirements For Hvac Equipment | DLR L236 | Pro Air
66 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 05 13 | Common Motor Requirements For HVAC Equipment | 1.1 | Warranty - Manufacturer | For Motor Requirements For Hvac Equipment | DLR L236 | Pro Air
67 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 08 13 | Testing, Adjusting, And Balancing | 1.9 | O&M Data | For Air Systems | DLR L236 | Pro Air
68 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 08 13 | Testing, Adjusting, And Balancing | 1.1 | Warranty - Manufacturer | For Air Systems | DLR L236 | Pro Air
69 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 09 00 | Building Management System | 1.3 | Warranty - Contractor | Entire Control System - 1 Year | DLR L236 | Pro Air
70 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 09 00 | Building Management System | 1.5/D | Test-Reports | Testing And Commissioning Reports For Calibration Of Sensors, Loop Tuning Parameters, And Start Up Of The System | DLR L236 | Pro Air
71 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 09 00 | Building Management System | 1.6/B | O&M Data | Submit Manufacturer'S Agreement To Provide Necessary Programmed Maintenance And To Maintain Systems For One Year From Date Of Final Acceptance, Within Contract Sum | DLR L236 | Pro Air
72 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 23 00 | Refrigerant Piping | 1.7 | Attic Stock | For Refrigerant Piping | DLR L236 | Pro Air
73 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 23 00 | Refrigerant Piping | 1.9 | O&M Data | For Refrigerant Piping | DLR L236 | Pro Air
74 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 23 00 | Refrigerant Piping | 1.1 | Warranty - Manufacturer | For Refrigerant Piping | DLR L236 | Pro Air
75 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 1.7/B | Attic Stock | Fan-Powered-Unit Filters - One Spare Filter For Each Filter | DLR L236 | Pro Air
76 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 1.9 | O&M Data | For Air Terminal Units | DLR L236 | Pro Air
77 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 1.1 | Warranty - Manufacturer | For Air Terminal Units | DLR L236 | Pro Air
78 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 3.7 | Owner Training | Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Air Terminal Units | DLR L236 | Pro Air
79 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 74 13 | Packaged Rooftop Ventilation Unit | 1.5/C | O&M Data | Operation, And Maintenance Manuals | DLR L236 | Pro Air
80 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 74 13 | Packaged Rooftop Ventilation Unit | 1.5/D | Warranty - Sample/Special | 1. Full Parts And Labor Warranty - Atleast 1 Year 2. Compressors - 5 Years | DLR L236 | Pro Air
81 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.8/B/1 | Attic Stock | Filters - One Set(S) Of Filters For Each Indoor Cooling Unit | DLR L236 | Pro Air
82 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.9 | As-Builts | For Refrigerant Based Precision Cooling System | DLR L236 | Pro Air
83 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.1 | O&M Data | Of Refrigerant Based Precision Cooling System | DLR L236 | Pro Air
84 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.11 | Warranty - Contractor | For Refrigerant Based Precision Cooling System | DLR L236 | Pro Air
85 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 1.7 | Attic Stock | Of Humidifiers | DLR L236 | Pro Air
86 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 1.9 | O&M Data | Of Humidifiers | DLR L236 | Pro Air
87 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 1.1 | Warranty - Contractor | Of Humidifiers | DLR L236 | Pro Air
88 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 3.5 | Owner Training | Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Humidifiers. | DLR L236 | Pro Air
89 | 26 - Electrical | 26 00 10 | Basic Electrical Requirements | 1.7 | Attic Stock | Extra Materials For Products Mentioned | DLR L236 | Power Solutions
90 | 26 - Electrical | 26 00 10 | Basic Electrical Requirements | 1.9 | O&M Data | Provide Operating Instructions And Maintenance Data | DLR L236 | Power Solutions
91 | 26 - Electrical | 26 00 10 | Basic Electrical Requirements | 1.1 | Warranty - Manufacturer | Manufacturers Shall Provide Their Standard Warranties For Material And Equipment Furnished | DLR L236 | Power Solutions
92 | 26 - Electrical | 26 05 00 | Common Work Results For Electrical | 1.9 | Attic Stock | Extra Materials For Products Mentioned | DLR L236 | Power Solutions
93 | 26 - Electrical | 26 05 00 | Common Work Results For Electrical | 1.9 | O&M Data | Provide All The Required Operation And Maintenance Data | DLR L236 | Power Solutions
94 | 26 - Electrical | 26 05 00 | Common Work Results For Electrical | 1.1 | Warranty - Manufacturer | Warranty Must Be Provided For All The Common Work Results For Electrical | DLR L236 | Power Solutions
95 | 26 - Electrical | 26 05 19 | Electrical Power Conductors And Cables (600 Volts Or Less) | 1.7 | Attic Stock | Of Electrical Power Conductors And Cables | DLR L236 | Power Solutions
96 | 26 - Electrical | 26 05 19 | Electrical Power Conductors And Cables (600 Volts Or Less) | 1.9 | O&M Data | Of Electrical Power Conductors And Cables | DLR L236 | Power Solutions
97 | 26 - Electrical | 26 05 19 | Electrical Power Conductors And Cables (600 Volts Or Less) | 1.1 | Warranty - Manufacturer | For Electrical Power Conductors And Cables | DLR L236 | Power Solutions
98 | 26 - Electrical | 26 05 26 | Grounding | 1.7 | Attic Stock | Provide Extra Materials For Grounding | DLR L236 | Power Solutions
99 | 26 - Electrical | 26 05 26 | Grounding | 1.8 | Test-Reports | Reports Of Service Ground Resistance And Resistance Readings From Ground Bar To Ground Bar And From Srg To Raised Floor | DLR L236 | Power Solutions
100 | 26 - Electrical | 26 05 26 | Grounding | 1.8 | O&M Data | Of Grounding | DLR L236 | Power Solutions
101 | 26 - Electrical | 26 05 26 | Grounding | 1.1 | Warranty - Manufacturer | For Grounding | DLR L236 | Power Solutions
102 | 26 - Electrical | 26 05 29 | Hangers And Supports For Electrical Systems | 1.7 | Attic Stock | Of Hangers And Supports For Electrcial Systems | DLR L236 | Power Solutions
103 | 26 - Electrical | 26 05 29 | Hangers And Supports For Electrical Systems | 1.9 | O&M Data | Of Hangers And Supports For Electrcial Systems | DLR L236 | Power Solutions
104 | 26 - Electrical | 26 05 29 | Hangers And Supports For Electrical Systems | 1.1 | Warranty - Manufacturer | For Hangers And Supports For Electrcial Systems | DLR L236 | Power Solutions
105 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.7 | Attic Stock | Raceway And Boxes Extra Material For Electrcial Systems | DLR L236 | Power Solutions
106 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.8/B/1 | As-Builts | Accurately Record With Dimensions On As-Built Drawings The Locations Of All Concealed Raceways | DLR L236 | Power Solutions
107 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.9 | O&M Data | Of Raceway And Boxes For Electrcial Systems | DLR L236 | Power Solutions
108 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.1 | Warranty - Manufacturer | Warranty Of Raceway And Boxes For Electrcial Systems | DLR L236 | Power Solutions
109 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 1.7 | Attic Stock | Of Cable Trays | DLR L236 | Power Solutions
110 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 1.9 | O&M Data | Of Cable Trays | DLR L236 | Power Solutions
111 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 1.1 | Warranty - Manufacturer | Of Cable Trays | DLR L236 | Power Solutions
112 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 3.5/B | Test-Reports | Report Field Quality Control Results In Writing After Installation | DLR L236 | Power Solutions
113 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 1.9 | Attic Stock | Of Cable Trough | DLR L236 | Power Solutions
114 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 1.11 | O&M Data | Of Cable Trough | DLR L236 | Power Solutions
115 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 1.12 | Warranty - Manufacturer | Of Cable Trough | DLR L236 | Power Solutions
116 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 3.5/B | Test-Reports | Report Field Quality Control Results In Writing After Installation | DLR L236 | Power Solutions
117 | 26 - Electrical | 26 05 38 | Cable Bus For Electrical Systems | 1.7 | Attic Stock | Of Cable Bus | DLR L236 | Power Solutions
118 | 26 - Electrical | 26 05 38 | Cable Bus For Electrical Systems | 1.9 | O&M Data | Operation And Maintenance Data For Cable Bus | DLR L236 | Power Solutions
119 | 26 - Electrical | 26 05 38 | Cable Bus For Electrical Systems | 1.1 | Warranty - Manufacturer | Of Cable Bus | DLR L236 | Power Solutions
120 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.6/M | Test-Reports | Source Quality-Control Test Reports | DLR L236 | Power Solutions
121 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.7/A | Attic Stock | Underground Ducts And Raceways For Electrical Systems | DLR L236 | Power Solutions
122 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.8/B | As-Builts | As-Built Drawings | DLR L236 | Power Solutions
123 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.9 | O&M Data | Underground Ducts And Raceways For Electrical Systems | DLR L236 | Power Solutions
124 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.10 | Warranty - Manufacturer | Underground Ducts And Raceways For Electrical Systems | DLR L236 | Power Solutions
125 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.6/I | Test-Reports | Field Quality-Control Test Reports | DLR L236 | Power Solutions
126 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.7 | Attic Stock | Vibration And Seismic Controls For Electrical Systems | DLR L236 | Power Solutions
127 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.9 | O&M Data | Vibration And Seismic Controls For Electrical Systems | DLR L236 | Power Solutions
128 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.10 | Warranty - Manufacturer | Vibration And Seismic Controls For Electrical Systems | DLR L236 | Power Solutions
129 | 26 - Electrical | 26 05 53 | Identification For Electrical Systems | 1.7 | Attic Stock | Identification For Electrical Systems | DLR L236 | Power Solutions
130 | 26 - Electrical | 26 05 53 | Identification For Electrical Systems | 1.9 | O&M Data | Identification For Electrical Systems | DLR L236 | Power Solutions
131 | 26 - Electrical | 26 05 53 | Identification For Electrical Systems | 1.10 | Warranty - Manufacturer | Identification For Electrical Systems | DLR L236 | Power Solutions
132 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 1.7 | Attic Stock | Testing Of Electrical Systems | DLR L236 | Power Solutions
133 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 1.9 | O&M Data | Testing Of Electrical Systems | DLR L236 | Power Solutions
134 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 1.10 | Warranty - Manufacturer | Testing Of Electrical Systems | DLR L236 | Power Solutions
135 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 3.13 | Test-Reports | Electrical Systems | DLR L236 | Power Solutions
136 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 1.7 | Attic Stock | Lighting Control Devices | DLR L236 | Power Solutions
137 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 1.9 | O&M Data | Lighting Control Devices | DLR L236 | Power Solutions
138 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 1.10 | Warranty - Manufacturer | Lighting Control Devices | DLR L236 | Power Solutions
139 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 3.7/B | Owner Training | Train Owner'S Maintenance Personnel | DLR L236 | Power Solutions
140 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.6/D | Test-Reports | Low-Voltage Transformers | DLR L236 | Power Solutions
141 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.7 | Attic Stock | Low-Voltage Transformers | DLR L236 | Power Solutions
142 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.9 | O&M Data | Low-Voltage Transformers | DLR L236 | Power Solutions
143 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.10 | Warranty - Manufacturer | Low-Voltage Transformers | DLR L236 | Power Solutions
144 | 26 - Electrical | 26 24 13i | Switchboards - Install | 1.7 | Attic Stock | Switchboards - Install | DLR L236 | Power Solutions
145 | 26 - Electrical | 26 24 13i | Switchboards - Install | 1.9 | O&M Data | Switchboards - Install | DLR L236 | Power Solutions
146 | 26 - Electrical | 26 24 13i | Switchboards - Install | 1.10 | Warranty - Manufacturer | Switchboards - Install | DLR L236 | Power Solutions
147 | 26 - Electrical | 26 24 13i | Switchboards - Install | 3.5 | Test-Reports | Field Quality Control | DLR L236 | Power Solutions
148 | 26 - Electrical | 26 24 13i | Switchboards - Install | 3.8/A | Owner Training | Train Owner'S Maintenance Personnel | DLR L236 | Power Solutions
149 | 26 - Electrical | 26 24 16 | Panelboards | 1.7 | Attic Stock | 1. 6 Of Each Panelboard Key 2. 2 Spare Circuit Breaker Lock-On Devices For Each Panelboard 3. Three Spare Circuit Breakers For Each Size And Type | DLR L236 | Power Solutions
150 | 26 - Electrical | 26 24 16 | Panelboards | 1.9/B | O&M Data | Maintenance Data | DLR L236 | Power Solutions
151 | 26 - Electrical | 26 24 16 | Panelboards | 1.10 | Warranty - Manufacturer | Panelboards | DLR L236 | Power Solutions
152 | 26 - Electrical | 26 24 16 | Panelboards | 3.4 | Test-Reports | Field Quality Control | DLR L236 | Power Solutions
153 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 1.7 | Attic Stock | Of Power Distribution Units | DLR L236 | Power Solutions
154 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 1.9 | O&M Data | Of Power Distribution Units | DLR L236 | Power Solutions
155 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 1.1 | Warranty - Manufacturer | Of Power Distribution Units | DLR L236 | Power Solutions
156 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 3.5/C | Test-Reports | Submit Documentation Of Tests And Inspections, Along With Manufacturers' Written Instructions And Other Test And Inspection Criteria | DLR L236 | Power Solutions
157 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 3.9 | Owner Training | Assist Factory-Authorized Service Representative To Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Power Distribution Units | DLR L236 | Power Solutions
158 | 26 - Electrical | 26 27 26 | Wiring Devices | 1.7 | Attic Stock | Of Wiring Devices | DLR L236 | Power Solutions
159 | 26 - Electrical | 26 27 26 | Wiring Devices | 1.9 | O&M Data | Of Wiring Devices | DLR L236 | Power Solutions
160 | 26 - Electrical | 26 27 26 | Wiring Devices | 1.1 | Warranty - Manufacturer | Of Wiring Devices | DLR L236 | Power Solutions
161 | 26 - Electrical | 26 27 26 | Wiring Devices | 3.4 | Test-Reports | Field Quality Control Tests And Inspection Reports | DLR L236 | Power Solutions
162 | 26 - Electrical | 26 28 13 | Fuses | 1.7 | Attic Stock | 1. 600 Ampere And Smaller: 10 Percent Of Each Rating (Minimum Of 3 Per Rating) 2. 601 Ampere And Larger: 3 Of Each Rating 3. Fuse Pullers: Provide 2 Of Each Type Required 4. Spare Fuse Cabinets | DLR L236 | Power Solutions
163 | 26 - Electrical | 26 28 13 | Fuses | 1.8/B | As-Builts | Record On Final Drawings Actual Fuse Sizes And Types Installed, Adjacent To Each Device | DLR L236 | Power Solutions
164 | 26 - Electrical | 26 28 13 | Fuses | 1.9 | O&M Data | Of Fuses | DLR L236 | Power Solutions
165 | 26 - Electrical | 26 28 13 | Fuses | 1.1 | Warranty - Manufacturer | Of Fuses | DLR L236 | Power Solutions
166 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 1.7/B | Attic Stock | A. Spares: 10% Of Installed With A Minimum Of 3 Per Size, For The Following: 1) Control-Power Fuses 2) Fuses For Fused Switches 3) Fuses For Fused Power-Circuit Devices B. Spare Indicating Lights: Six Of Each Type Installed | DLR L236 | Power Solutions
167 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 1.9 | O&M Data | Of Enclosed Switches And Circuit Breakers | DLR L236 | Power Solutions
168 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 1.1 | Warranty - Manufacturer | Of Enclosed Switches And Circuit Breakers | DLR L236 | Power Solutions
169 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 3.5/G | Test-Reports | Field Quality Control Tests And Inspection Reports Including A Certified Report That Identifies Enclosed Switches And Circuit Breakers | DLR L236 | Power Solutions
170 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.6/B | Test-Reports | Written Test Results | DLR L236 | Power Solutions
171 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.7/B | Attic Stock | 1. One Spare Set Of Consumables Such As Fuses, Filters, Etc. 2. One Spare Set Of Air, Fuel And Oil Filters In Addition To Those To Be Installed After Acceptance And Integrated Systems Testing | DLR L236 | Power Solutions
172 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.9 | O&M Data | Of Engine Generators | DLR L236 | Power Solutions
173 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.1 | Warranty - Manufacturer | Of Engine Generators | DLR L236 | Power Solutions
174 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 3.5/A | Test-Reports | Field Quality Control Tests And Inspection Reports | DLR L236 | Power Solutions
175 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 3.6/A | Owner Training | Assist Factory-Authorized Service Representative To Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Packaged Engine Generators | DLR L236 | Power Solutions
176 | 26 - Electrical | 26 32 15 | Engine Generator Field Startup Requirements | 1.7 | Attic Stock | 1. One Spare Set Of Consumables Such As Fuses, Filters, Etc. 2. One Spare Set Of Air, Fuel And Oil Filters In Addition To Those To Be Installed After Acceptance And Integrated Systems Testing | DLR L236 | Power Solutions
177 | 26 - Electrical | 26 32 15 | Engine Generator Field Startup Requirements | 3.4/A | Test-Reports | Oil Analysis Written Report | DLR L236 | Power Solutions
178 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 1.7 | Attic Stock | Static Uninterruptible Power Supply - Install | DLR L236 | Power Solutions
179 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 1.9 | O&M Data | Static Uninterruptible Power Supply - Install | DLR L236 | Power Solutions
180 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | Power Solutions
181 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 3.9/A | Owner Training | Train Owner'S Maintenance Personnel | DLR L236 | Power Solutions
182 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.6/E | Attic Stock | Field Quality-Control Reports | DLR L236 | Power Solutions
183 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.7 | Attic Stock | Lightning Protection For Structures | DLR L236 | Power Solutions
184 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.8/B | As-Builts | As-Built Drawings | DLR L236 | Power Solutions
185 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.9 | O&M Data | Lightning Protection For Structures | DLR L236 | Power Solutions
186 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | Power Solutions
187 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 1.7 | Attic Stock | One Set Of Spare Fuses Of Each Type Used | DLR L236 | Power Solutions
188 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 1.9 | O&M Data | Surge Protective Devices | DLR L236 | Power Solutions
189 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 1.10/A | Warranty - Manufacturer | Surge Protective Devices | DLR L236 | Power Solutions
190 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 3.5/A | Owner Training | Train Owner'S Maintenance Personnel To Maintain Spd Devices | DLR L236 | Power Solutions
191 | 26 - Electrical | 26 51 00 | Lighting | 1.7 | Attic Stock | 1. Provide Two Of Each Plastic Lens 2. Provide One Case (Minimum Of 12) Replacement Lamps For Each Type Of Lamp And Wattage Installed. Provide Five Cases (60 Lamps) Of Four-Foot Fluorescent Lamps 3. Provide Two Of Each Ballast Type And Rating 4. Provide Spare Fuses For Fused Fixtures Equal To 10% Of Total Installed Of Each Type | DLR L236 | Power Solutions
192 | 26 - Electrical | 26 51 00 | Lighting | 1.9 | O&M Data | Lighting | DLR L236 | Power Solutions
193 | 26 - Electrical | 26 51 00 | Lighting | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | Power Solutions
194 | 26 - Electrical | 26 51 00 | Lighting | 3.7/B | Owner Training | Demonstration Of Luminaire Operation - 2 Hours | DLR L236 | Power Solutions
195 | 27 - Communications | 27 05 26 | Grounding And Bonding For Communications Systems | 1.7 | Attic Stock | Grounding And Bonding For Communications Systems | DLR L236 | TBD
196 | 27 - Communications | 27 05 26 | Grounding And Bonding For Communications Systems | 1.9 | O&M Data | Grounding And Bonding For Communications Systems | DLR L236 | TBD
197 | 27 - Communications | 27 05 26 | Grounding And Bonding For Communications Systems | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | TBD
198 | 27 - Communications | 27 05 28 | Low Voltage Raceway Systems | 1.7 | Attic Stock | Low Voltage Raceway Systems | DLR L236 | TBD
199 | 27 - Communications | 27 05 28 | Low Voltage Raceway Systems | 1.9 | O&M Data | Low Voltage Raceway Systems | DLR L236 | TBD
200 | 28 - Electronic Safety And Security | 28 08 00 | Security Systems Commissioning | 1.04/2 | O&M Data | Security Systems Commissioning | DLR L236 | AVS Technology
201 | 28 - Electronic Safety And Security | 28 08 00 | Security Systems Commissioning | 3.04/A | As-Builts | Detailed Wiring Diagram | DLR L236 | AVS Technology
202 | 28 - Electronic Safety And Security | 28 08 00 | Security Systems Commissioning | 3.05/A | Owner Training | Owner Instruction In The Operation And Testing Of The System | DLR L236 | AVS Technology
203 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.6/D | Test-Reports | Satisfactory Completion Of Required Tests And Inspections | DLR L236 | AVS Technology
204 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.7 | Attic Stock | 1. Ten Manual Station Break-Glass Rods 2. Six Keys Of Each Type 3. Three Of Each Type Of Automatic Smoke Detector | DLR L236 | AVS Technology
205 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.9 | O&M Data | Digital, Addressable Fire-Alarm System - Tkd | DLR L236 | AVS Technology
206 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | AVS Technology
207 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 3.7/A | Owner Training | Rain Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Fire-Alarm System | DLR L236 | AVS Technology

## Guide
Guideline for more filter
For More filter :-
1) | Click on any slicer
2) | Go to slicer tool option on Ribbon (Snapshot 2) > Selection Pan > click on the filter with "-" sign (Snapshot 3)
3)
Snap2
Snapshot 2
4)
Snapshot 3

## Sheet4 (hidden)
Trade Partener | Reveived Documents | Pending Documents | Voided Documents | Spec Name & Number
0 |  | 0 |  | 0_0
Total
0 Total
|  | Warranty - Sample/Special |  | 01 78 36 _Warranties
Total
Warranty - Sample/Special Total
|  | Warranty - Manufacturer |  | 01 73 29_Cutting And Patching
01 78 00_Closeout Submittals
01 78 36 _Warranties
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 01 50 00_Temporary Facilities And Controls
01 78 00_Closeout Submittals
Total
Test-Reports Total
|  | O&M Data |  | 01 78 00_Closeout Submittals
Total
O&M Data Total
|  | Owner Training |  | 01 79 00_Demonstration And Training
Total
Owner Training Total
|  | As-Builts |  | 01 78 00_Closeout Submittals
Total
As-Builts Total
Total
0 Total
K&A Contracting |  | Test-Reports |  | 03 01 36_Resurfacing And Patching Of Concrete Slabs
03 30 00_Cast-In-Place Concrete
Total
Test-Reports Total
Total
K&A Contracting Total
Hallmark |  | Test-Reports |  | 05 12 00_Structural Steel Framing
Total
Test-Reports Total
|  | Other |  | 05 50 00 _Metal Fabrications
Total
Other Total
Total
Hallmark Total
American Automatic FP |  | Warranty - Sample/Special |  | 07 6200_Sheet Metal Flashing And Trim
Total
Warranty - Sample/Special Total
|  | Warranty - Manufacturer |  | 07 59 00 _Cutting And Patching Membrane Roofing
07 72 00_Roof Accessories
07 92 00_Joint Sealents
21 00 10_Basic Fire Protection Requirements
21 01 00_Sprinkler Systems
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 07 59 00 _Cutting And Patching Membrane Roofing
07 84 00_Firestopping
Total
Test-Reports Total
|  | O&M Data |  | 21 00 10_Basic Fire Protection Requirements
21 01 00_Sprinkler Systems
Total
O&M Data Total
|  | Owner Training |  | 21 00 10_Basic Fire Protection Requirements
21 01 00_Sprinkler Systems
Total
Owner Training Total
|  | Attic Stock |  | 21 00 10_Basic Fire Protection Requirements
21 01 00_Sprinkler Systems
Total
Attic Stock Total
Total
American Automatic FP Total
Precision |  | Warranty - Sample/Special |  | 08 70 00_Hardware
Total
Warranty - Sample/Special Total
|  | Warranty - Manufacturer |  | 08 11 13_Hollow Metal Doors And Frames
08 80 00_Glazing
08 91 00_Louvers
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 08 91 00_Louvers
Total
Test-Reports Total
|  | O&M Data |  | 08 70 00_Hardware
Total
O&M Data Total
|  | Other |  | 08 70 00_Hardware
Total
Other Total
|  | Owner Training |  | 08 70 00_Hardware
Total
Owner Training Total
|  | Keys |  | 08 70 00_Hardware
Total
Keys Total
Total
Precision Total
Capital City Flooring |  | Warranty - Manufacturer |  | 09 51 00_Acoustical Ceilings
09 65 13_Resilient Base And Accessories
09 69 00_Access Flooring
Total
Warranty - Manufacturer Total
|  | O&M Data |  | 09 69 00_Access Flooring
Total
O&M Data Total
|  | Attic Stock |  | 09 51 00_Acoustical Ceilings
09 65 13_Resilient Base And Accessories
Total
Attic Stock Total
Total
Capital City Flooring Total
Capitol Coatings |  | Warranty - Manufacturer |  | 09 97 26_Exterior Textured Coatings
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 09 97 26_Exterior Textured Coatings
Total
Test-Reports Total
|  | Attic Stock |  | 09 69 00_Access Flooring
Total
Attic Stock Total
|  | Mockups |  | 09 91 00_Painting
Total
Mockups Total
Total
Capitol Coatings Total
Pro Air |  | Warranty - Sample/Special |  | 23 74 13_Packaged Rooftop Ventilation Unit
Total
Warranty - Sample/Special Total
|  | Warranty - Manufacturer |  | 22 00 10_Basic Plumbing Requirement
22 01 00_Plumbing Systems
23 00 10_General Mechanical Requirements
23 05 13_Common Motor Requirements For HVAC Equipment
23 08 13_Testing, Adjusting, And Balancing
23 23 00_Refrigerant Piping
23 36 00_Air Terminal Units
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 22 01 00_Plumbing Systems
23 00 10_General Mechanical Requirements
23 09 00_Building Management System
Total
Test-Reports Total
|  | O&M Data |  | 22 00 10_Basic Plumbing Requirement
23 05 13_Common Motor Requirements For HVAC Equipment
23 08 13_Testing, Adjusting, And Balancing
23 09 00_Building Management System
23 23 00_Refrigerant Piping
23 36 00_Air Terminal Units
23 74 13_Packaged Rooftop Ventilation Unit
23 81 25_Refrigerant Based Precision Cooling System
23 84 13_Humidifiers
Total
O&M Data Total
|  | Other |  | 22 01 00_Plumbing Systems
Total
Other Total
|  | Owner Training |  | 22 00 10_Basic Plumbing Requirement
23 36 00_Air Terminal Units
23 84 13_Humidifiers
Total
Owner Training Total
|  | As-Builts |  | 23 81 25_Refrigerant Based Precision Cooling System
Total
As-Builts Total
|  | Attic Stock |  | 22 00 10_Basic Plumbing Requirement
23 00 10_General Mechanical Requirements
23 05 13_Common Motor Requirements For HVAC Equipment
23 23 00_Refrigerant Piping
23 36 00_Air Terminal Units
23 81 25_Refrigerant Based Precision Cooling System
23 84 13_Humidifiers
Total
Attic Stock Total
|  | Warranty - Installer |  | 22 01 00_Plumbing Systems
Total
Warranty - Installer Total
|  | Warranty - Contractor |  | 23 09 00_Building Management System
23 81 25_Refrigerant Based Precision Cooling System
23 84 13_Humidifiers
Total
Warranty - Contractor Total
Total
Pro Air Total
Power Solutions |  | Warranty - Manufacturer |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems
26 05 48_Vibration And Seismic Controls For Electrical Systems
26 05 53_Identification For Electrical Systems
26 08 13_Testing Of Electrical Systems
26 09 23_Lighting Control Devices
26 22 00_Low-Voltage Transformers
26 24 13i _Switchboards - Install
26 00 10_Basic Electrical Requirements
26 05 00_Common Work Results For Electrical
26 05 19_Electrical Power Conductors And Cables (600 Volts Or Less)
26 05 26_Grounding
26 05 29_Hangers And Supports For Electrical Systems
26 05 33_Raceway And Boxes For Electrical Systems
26 05 36_Cable Trays For Electrical Systems
26 05 37_Cable Trough For Electrical Systems
26 05 38_Cable Bus For Electrical Systems
26 24 16_Panelboards
26 26 00i_Power Distribution Units - Install
26 27 26_Wiring Devices
26 28 13_Fuses
26 28 16_Enclosed Switches And Circuit Breakers
26 32 13i_Engine Generators - Install
26 33 53i_Static Uninterruptible Power Supply - Install
26 41 13_Lightning Protection For Structures
26 43 13_Surge Protective Devices
26 51 00_Lighting
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems
26 05 48_Vibration And Seismic Controls For Electrical Systems
26 08 13_Testing Of Electrical Systems
26 22 00_Low-Voltage Transformers
26 24 13i _Switchboards - Install
26 05 26_Grounding
26 05 36_Cable Trays For Electrical Systems
26 05 37_Cable Trough For Electrical Systems
26 24 16_Panelboards
26 26 00i_Power Distribution Units - Install
26 27 26_Wiring Devices
26 28 16_Enclosed Switches And Circuit Breakers
26 32 13i_Engine Generators - Install
26 32 15_Engine Generator Field Startup Requirements
Total
Test-Reports Total
|  | O&M Data |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems
26 05 48_Vibration And Seismic Controls For Electrical Systems
26 05 53_Identification For Electrical Systems
26 08 13_Testing Of Electrical Systems
26 09 23_Lighting Control Devices
26 22 00_Low-Voltage Transformers
26 24 13i _Switchboards - Install
26 00 10_Basic Electrical Requirements
26 05 00_Common Work Results For Electrical
26 05 19_Electrical Power Conductors And Cables (600 Volts Or Less)
26 05 26_Grounding
26 05 29_Hangers And Supports For Electrical Systems
26 05 33_Raceway And Boxes For Electrical Systems
26 05 36_Cable Trays For Electrical Systems
26 05 37_Cable Trough For Electrical Systems
26 05 38_Cable Bus For Electrical Systems
26 24 16_Panelboards
26 26 00i_Power Distribution Units - Install
26 27 26_Wiring Devices
26 28 13_Fuses
26 28 16_Enclosed Switches And Circuit Breakers
26 32 13i_Engine Generators - Install
26 33 53i_Static Uninterruptible Power Supply - Install
26 41 13_Lightning Protection For Structures
26 43 13_Surge Protective Devices
26 51 00_Lighting
Total
O&M Data Total
|  | Owner Training |  | 26 09 23_Lighting Control Devices
26 24 13i _Switchboards - Install
26 26 00i_Power Distribution Units - Install
26 32 13i_Engine Generators - Install
26 33 53i_Static Uninterruptible Power Supply - Install
26 43 13_Surge Protective Devices
26 51 00_Lighting
Total
Owner Training Total
|  | As-Builts |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems
26 05 33_Raceway And Boxes For Electrical Systems
26 28 13_Fuses
26 41 13_Lightning Protection For Structures
Total
As-Builts Total
|  | Attic Stock |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems
26 05 48_Vibration And Seismic Controls For Electrical Systems
26 05 53_Identification For Electrical Systems
26 08 13_Testing Of Electrical Systems
26 09 23_Lighting Control Devices
26 22 00_Low-Voltage Transformers
26 24 13i _Switchboards - Install
26 00 10_Basic Electrical Requirements
26 05 00_Common Work Results For Electrical
26 05 19_Electrical Power Conductors And Cables (600 Volts Or Less)
26 05 26_Grounding
26 05 29_Hangers And Supports For Electrical Systems
26 05 33_Raceway And Boxes For Electrical Systems
26 05 36_Cable Trays For Electrical Systems
26 05 37_Cable Trough For Electrical Systems
26 05 38_Cable Bus For Electrical Systems
26 24 16_Panelboards
26 26 00i_Power Distribution Units - Install
26 27 26_Wiring Devices
26 28 13_Fuses
26 28 16_Enclosed Switches And Circuit Breakers
26 32 13i_Engine Generators - Install
26 32 15_Engine Generator Field Startup Requirements
26 33 53i_Static Uninterruptible Power Supply - Install
26 41 13_Lightning Protection For Structures
26 43 13_Surge Protective Devices
26 51 00_Lighting
Total
Attic Stock Total
Total
Power Solutions Total
AVS Technology |  | Warranty - Manufacturer |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD
Total
Test-Reports Total
|  | O&M Data |  | 28 08 00_Security Systems Commissioning
28 31 12_Digital, Addressable Fire-Alarm System - TKD
Total
O&M Data Total
|  | Owner Training |  | 28 08 00_Security Systems Commissioning
28 31 12_Digital, Addressable Fire-Alarm System - TKD
Total
Owner Training Total
|  | As-Builts |  | 28 08 00_Security Systems Commissioning
Total
As-Builts Total
|  | Attic Stock |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD
Total
Attic Stock Total
Total
AVS Technology Total
TBD |  | Warranty - Manufacturer |  | 27 05 26_Grounding And Bonding For Communications Systems
Total
Warranty - Manufacturer Total
|  | Test-Reports |  | 04 20 00_Unit Masonary
Total
Test-Reports Total
|  | O&M Data |  | 27 05 26_Grounding And Bonding For Communications Systems
27 05 28_Low Voltage Raceway Systems
Total
O&M Data Total
|  | Attic Stock |  | 27 05 26_Grounding And Bonding For Communications Systems
27 05 28_Low Voltage Raceway Systems
Total
Attic Stock Total
Total
TBD Total
Grand Total

## To be Hide (hidden)
S.NO | Division | Spec Number | Spec Name | Spec Sub Section | Document Type | Descriptions | Block/Building if any | Trade Partener | Comments | Submitted To DPR | Updated To EQX Box Folder | Helper 1 | Reveived Documents | Helper | Pending Documents | Voided Documents | Spec Name & Number | text
1 | 01 - General Requirements | 01 50 00 | Temporary Facilities And Controls | 1.3/A/1 | Test-Reports | Temporary Utilities | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 01 50 00_Temporary Facilities And Controls | 1
2 | 01 - General Requirements | 01 73 29 | Cutting And Patching | 1.5/A | Warranty - Manufacturer | Standard Product Warranties | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 01 73 29_Cutting And Patching | 2
3 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/2 | As-Builts | 1. Project Record Drawings - 2 Sets Of Drawings 2. Blackline Print Drawings - 1 Set | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | As-Builts |  | 01 78 00_Closeout Submittals | 3
4 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/4,6 | O&M Data | 1. Preventive Maintenance Instructions - 3 Bound Copies 2. Maintenance Contracts - 2 Copies | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 01 78 00_Closeout Submittals | 4
5 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/5 | Warranty - Manufacturer | Product Warranties And Bonds - 2 Copies | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 01 78 00_Closeout Submittals | 5
6 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.4/A/7 | Test-Reports | Record Of All Test Reports And Inspections - 4 Copies | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 01 78 00_Closeout Submittals | 6
7 | 01 - General Requirements | 01 78 00 | Closeout Submittals | 1.7/A | O&M Data | 1. Fire Protection System. 2. Utilities And Plumbing Systems. 3. Heating, Ventilation And Air Conditioning System. 4. Electrical Systems. | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 01 78 00_Closeout Submittals | 7
8 | 01 - General Requirements | 01 78 36 | Warranties | 1.3 | Warranty - Manufacturer | Standard Product Warranties | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 01 78 36 _Warranties | 8
9 | 01 - General Requirements | 01 78 36 | Warranties | 1.4 | Warranty - Sample/Special | Special Warranties | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | Warranty - Sample/Special |  | 01 78 36 _Warranties | 9
10 | 01 - General Requirements | 01 79 00 | Demonstration And Training | 1.3 | Owner Training | 1. General Overview Of Record Documents - Not Less Than 3 Hours 2. Fire Protection Systems And Equipment: Not Less Than 6 Hours 3. Fire Alarms Systems And Equipment: Not Less Than 8 Hours 4. Hvac Systems And Equipment: Not Less Than 32 Hours 5. Plumbing Systems And Equipment: Not Less Than 6 Hours 6. Electrical Systems And Equipment (Including Emergency Generator): Not Less Than 32 Hours 7. Audio-Visual Systems, Sound Systems And Similar Equipment: Not Less Than 4 Hours 8. Other Utility Connected Systems, Control Systems, Security Systems, And Similar Equipment: Not Less Than 8 Hours | DLR L236 | 0 | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 01 79 00_Demonstration And Training | 10
11 | 03 - Concrete | 03 01 36 | Resurfacing And Patching Of Concrete Slabs | 1.4/A/2 | Test-Reports | Preliminary Design Mix Reports | DLR L236 | K&A Contracting | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 03 01 36_Resurfacing And Patching Of Concrete Slabs | 11
12 | 03 - Concrete | 03 30 00 | Cast-In-Place Concrete | 1.5 | Test-Reports | 1. Aggregates 2. Field Quality-Control Reports | DLR L236 | K&A Contracting | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 03 30 00_Cast-In-Place Concrete | 12
13 | 04 - Masonary | 04 20 00 | Unit Masonary | 1.4/A/3 | Test-Reports | 1. Mortar 2. Grout Mixes 3. Masonary Units | DLR L236 | TBD | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 04 20 00_Unit Masonary | 13
14 | 05 - Metals | 05 12 00 | Structural Steel Framing | 1.6 | Test-Reports | 1. Mill Test Reports For Structural Steel 2. Bolts, Nuts, And Washers 3. Direct-Tension Indicators 4. Tension-Control, High-Strength Bolt-Nut-Washer Assemblies | DLR L236 | Hallmark | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 05 12 00_Structural Steel Framing | 14
15 | 05 - Metals | 05 50 00 | Metal Fabrications | 1.5/B/1 | Other | Special Inspections | DLR L236 | Hallmark | 0 | 0 | 0 |  |  | 1 | Other |  | 05 50 00 _Metal Fabrications | 15
16 | 07 - Thermal And Moisture Protections | 07 59 00 | Cutting And Patching Membrane Roofing | 1.4/B/1 | Test-Reports | Manufacturer’S Field Quality Control Reports Of Field Inspections | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 07 59 00 _Cutting And Patching Membrane Roofing | 16
17 | 07 - Thermal And Moisture Protections | 07 59 00 | Cutting And Patching Membrane Roofing | 1.4/B/2 | Warranty - Manufacturer | Manufacturer’S Warranties | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 07 59 00 _Cutting And Patching Membrane Roofing | 17
18 | 07 - Thermal And Moisture Protections | 07 59 00 | Cutting And Patching Membrane Roofing | 1.9/A | Warranty - Manufacturer | For Membrane Roofing - 20 Years | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 07 59 00 _Cutting And Patching Membrane Roofing | 18
19 | 07 - Thermal And Moisture Protection | 07 6200 | Sheet Metal Flashing And Trim | 1.7/A/1 | Warranty - Sample/Special | Exposed Panel Finish - 20 Years | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Warranty - Sample/Special |  | 07 6200_Sheet Metal Flashing And Trim | 19
20 | 07 - Thermal And Moisture Protection | 07 72 00 | Roof Accessories | 1.8/A | Warranty - Manufacturer | Roof Accessories - 5 Years | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 07 72 00_Roof Accessories | 20
21 | 07 - Thermal And Moisture Protection | 07 84 00 | Firestopping | 1.5/A/4 | Test-Reports | Fire Stop Material | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 07 84 00_Firestopping | 21
22 | 07 - Thermal And Moisture Protection | 07 92 00 | Joint Sealents | 1.8/A | Warranty - Manufacturer | Installed Sealent And Accessories - 5 Years | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 07 92 00_Joint Sealents | 22
23 | 08 - Openings | 08 11 13 | Hollow Metal Doors And Frames | 1.5/B/1 | Warranty - Manufacturer | Hollow Metal And Door Frames | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 08 11 13_Hollow Metal Doors And Frames | 23
24 | 08 - Openings | 08 70 00 | Hardware | 1.3/H | Keys | Submit 6 Copies Of Keying Schedule Indicating Door Numbers In Numerical Sequence, And Its Particular Keying | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Keys |  | 08 70 00_Hardware | 24
25 | 08 - Openings | 08 70 00 | Hardware | 1.3/I/2 | O&M Data | 2 Maintenance Manuals At Accaptance Of Work | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 08 70 00_Hardware | 25
26 | 08 - Openings | 08 70 00 | Hardware | 1.3/I/2/e | O&M Data | Manufacturer’S Maintenance Instruction And Maintenance Schedule | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 08 70 00_Hardware | 26
27 | 08 - Openings | 08 70 00 | Hardware | 1.3/I/2/g | Other | Manufacturer Bitting List | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Other |  | 08 70 00_Hardware | 27
28 | 08 - Openings | 08 70 00 | Hardware | 1.7/A/1 | Warranty - Sample/Special | 1.Hinges - (Life Of Building) 2.Continuous Hinges - 10 Years 3.Door Closers - 10 Years 4.Door Closers With Electric Or Pneumatic Components - 2 Years 5.Exit Devices - 3 Years 6.Remainder Of Hardware - 1 Year | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Warranty - Sample/Special |  | 08 70 00_Hardware | 28
29 | 08 - Openings | 08 70 00 | Hardware | 1.8/A/1 | Owner Training | Training For Proper Use, Servicing, Adjustment And Maintenance Of Door Hardware | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 08 70 00_Hardware | 29
30 | 08 - Openings | 08 70 00 | Hardware | 1.8/B/1 | O&M Data | Approximately 6 Months After Acceptance Of Work, Arrange To Have Installer Of Hardware In Company With Representatives Of Lock, Exit Device And Closer Manufacturers Contact Owner And Make Arrangements For An Inspection Of Hardware. | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 08 70 00_Hardware | 30
31 | 08 - Openings | 08 80 00 | Glazing | 1.9/B/1 | Warranty - Manufacturer | Laminated Glass - 4 Years | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 08 80 00_Glazing | 31
32 | 08 - Openings | 08 91 00 | Louvers | 1.4/E | Test-Reports | Louvers Performance Criteria | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 08 91 00_Louvers | 32
33 | 08 - Openings | 08 91 00 | Louvers | 1.6/B | Warranty - Manufacturer | Finish - 20 Years | DLR L236 | Precision | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 08 91 00_Louvers | 33
34 | 09 - Finishes | 09 51 00 | Acoustical Ceilings | 1.10/A | Warranty - Manufacturer | All Furnished Materials | DLR L236 | Capital City Flooring | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 09 51 00_Acoustical Ceilings | 34
35 | 09 - Finishes | 09 51 00 | Acoustical Ceilings | 1.11/A | Attic Stock | Extra Ceiling Panel And Suspension Components - 3 % Of Each Type Installed | DLR L236 | Capital City Flooring | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 09 51 00_Acoustical Ceilings | 35
36 | 09 - Finishes | 09 65 13 | Resilient Base And Accessories | 1.5/B/1 | Attic Stock | Resilient Base - 24 Linear Feet | DLR L236 | Capital City Flooring | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 09 65 13_Resilient Base And Accessories | 36
37 | 09 - Finishes | 09 65 13 | Resilient Base And Accessories | 1.9/B | Warranty - Manufacturer | 1. Resilient Base - 1 Year 2. Adhesives - 1 Year | DLR L236 | Capital City Flooring | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 09 65 13_Resilient Base And Accessories | 37
38 | 09 - Finishes | 09 69 00 | Access Flooring | 1.5/B/1 | O&M Data | Data Including Recommended Cleaning Methods, Cleaning Materials Stain Removal Methods | DLR L236 | Capital City Flooring | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 09 69 00_Access Flooring | 38
39 | 09 - Finishes | 09 69 00 | Access Flooring | 1.12/A | Warranty - Manufacturer | Access Flooring - 5 Years | DLR L236 | Capital City Flooring | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 09 69 00_Access Flooring | 39
40 | 09 - Finishes | 09 69 00 | Access Flooring | 1.13/A | Attic Stock | 1. Floor Panel (Floor Tile) 2. Perforated Floor Panels (General Stock) - One Perforated Tile Per Every 4 Kw Of Ups Power Plus An Additional 5 Percent Stock 3. System “Af-1” Floor Panels - Sufficient Stock To Back Fill 75 Percent Of Perforated Tiles For Initial Build Out Of First Pod 4. System “Af-5” Floor Panels - 10 Floor Panels Per Computer Room 5. System “Af-6” Floor Panels - 10 Floor Panels Per Computer And Idf Room 6. Stringers - 25 Spare Stringers For Each System Type 7. Pedestals - 25 Spare Pedestals For Each System Type 8. Panel Lifting Devices - One Panel Lifting Device Per Door And An Additional Quantity Of One Per Every 1,500 Square Feet Of Access Flooring | DLR L236 | Capitol Coatings | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 09 69 00_Access Flooring | 40
41 | 09 - Finishes | 09 91 00 | Painting | 1.4/B/1 | Mockups | Color Chips | DLR L236 | Capitol Coatings | 0 | 0 | 0 |  |  | 1 | Mockups |  | 09 91 00_Painting | 41
42 | 09 - Finishes | 09 97 26 | Exterior Textured Coatings | 1.4/A/5 | Test-Reports | Compatibility And Adhesion Test Reports | DLR L236 | Capitol Coatings | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 09 97 26_Exterior Textured Coatings | 42
43 | 09 - Finishes | 09 97 26 | Exterior Textured Coatings | 1.8/A | Warranty - Manufacturer | Exterior Textured Coating | DLR L236 | Capitol Coatings | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 09 97 26_Exterior Textured Coatings | 43
44 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 1.7/A | Attic Stock | Provide Extra Material Under Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 21 00 10_Basic Fire Protection Requirements | 44
45 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 1.9/A | O&M Data | Provide Operating Instruction And Maintainence Data For Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 21 00 10_Basic Fire Protection Requirements | 45
46 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 1.10/A | Warranty - Manufacturer | Provide Warranty For Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 21 00 10_Basic Fire Protection Requirements | 46
47 | 21 - Fire Suppression | 21 00 10 | Basic Fire Protection Requirements | 3.3/C | Owner Training | Provide Owner Training For Each Specification Mentioned Under Fire Protection | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 21 00 10_Basic Fire Protection Requirements | 47
48 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 1.7/E | O&M Data | Submit Maintenance Instructions: Include Installation Instructions, Spare Parts Lists, Procedures, And Treatment Programs | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 21 01 00_Sprinkler Systems | 48
49 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 1.12/B/1 | Attic Stock | Sprinkler Cabinets - Minimum Of Six Spare Sprinklers Plus Sprinkler Wrench | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 21 01 00_Sprinkler Systems | 49
50 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 1.15 | Warranty - Manufacturer | For Sprinkler Systems | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 21 01 00_Sprinkler Systems | 50
51 | 21 - Fire Suppression | 21 01 00 | Sprinkler Systems | 3.15/A | Owner Training | Train Owner’S Maintenance Personnel To Adjust, Operate, And Maintain Specialty Valves | DLR L236 | American Automatic FP | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 21 01 00_Sprinkler Systems | 51
52 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 1.7/A | Attic Stock | Provide Extra Material Under Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 22 00 10_Basic Plumbing Requirement | 52
53 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 1.9/A | O&M Data | Provide Operating Instruction And Maintainence Data For Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 22 00 10_Basic Plumbing Requirement | 53
54 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 1.10/A | Warranty - Manufacturer | Provide Warranty For Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 22 00 10_Basic Plumbing Requirement | 54
55 | 22 - Plumbing | 22 00 10 | Basic Plumbing Requirement | 3.3/C | Owner Training | Provide Owner Training For Each Specification Mentioned Under Plumbing | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 22 00 10_Basic Plumbing Requirement | 55
56 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.5/C | Test-Reports | Field Quality-Control Inspection And Test Reports | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 22 01 00_Plumbing Systems | 56
57 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.5/D | Other | Record Drawings And Final Certification | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Other |  | 22 01 00_Plumbing Systems | 57
58 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.8/A | Warranty - Manufacturer | Standard Product | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 22 01 00_Plumbing Systems | 58
59 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.8/B | Warranty - Installer | For Plumbing Systems - 1 Year | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Installer |  | 22 01 00_Plumbing Systems | 59
60 | 22 - Plumbing | 22 01 00 | Plumbing Systems | 1.9/A | Other | Project Record Drawings | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Other |  | 22 01 00_Plumbing Systems | 60
61 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 00 10 | General Mechanical Requirements | 1.7 | Attic Stock | Extra Materials | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 23 00 10_General Mechanical Requirements | 61
62 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 00 10 | General Mechanical Requirements | 1.10/D | Warranty - Manufacturer | Guarantee Against All Defects In Materials And Workmanship For 1 Year | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 23 00 10_General Mechanical Requirements | 62
63 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 00 10 | General Mechanical Requirements | 3.4/C | Test-Reports | 1. Submit All Test Reports 2. Submit Local Authority Final Sign Off Inspection Reports | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 23 00 10_General Mechanical Requirements | 63
64 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 05 13 | Common Motor Requirements For HVAC Equipment | 1.7 | Attic Stock | For Motor Requirements For Hvac Equipment | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 23 05 13_Common Motor Requirements For HVAC Equipment | 64
65 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 05 13 | Common Motor Requirements For HVAC Equipment | 1.9 | O&M Data | For Motor Requirements For Hvac Equipment | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 05 13_Common Motor Requirements For HVAC Equipment | 65
66 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 05 13 | Common Motor Requirements For HVAC Equipment | 1.1 | Warranty - Manufacturer | For Motor Requirements For Hvac Equipment | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 23 05 13_Common Motor Requirements For HVAC Equipment | 66
67 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 08 13 | Testing, Adjusting, And Balancing | 1.9 | O&M Data | For Air Systems | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 08 13_Testing, Adjusting, And Balancing | 67
68 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 08 13 | Testing, Adjusting, And Balancing | 1.1 | Warranty - Manufacturer | For Air Systems | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 23 08 13_Testing, Adjusting, And Balancing | 68
69 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 09 00 | Building Management System | 1.3 | Warranty - Contractor | Entire Control System - 1 Year | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Contractor |  | 23 09 00_Building Management System | 69
70 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 09 00 | Building Management System | 1.5/D | Test-Reports | Testing And Commissioning Reports For Calibration Of Sensors, Loop Tuning Parameters, And Start Up Of The System | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 23 09 00_Building Management System | 70
71 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 09 00 | Building Management System | 1.6/B | O&M Data | Submit Manufacturer'S Agreement To Provide Necessary Programmed Maintenance And To Maintain Systems For One Year From Date Of Final Acceptance, Within Contract Sum | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 09 00_Building Management System | 71
72 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 23 00 | Refrigerant Piping | 1.7 | Attic Stock | For Refrigerant Piping | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 23 23 00_Refrigerant Piping | 72
73 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 23 00 | Refrigerant Piping | 1.9 | O&M Data | For Refrigerant Piping | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 23 00_Refrigerant Piping | 73
74 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 23 00 | Refrigerant Piping | 1.1 | Warranty - Manufacturer | For Refrigerant Piping | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 23 23 00_Refrigerant Piping | 74
75 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 1.7/B | Attic Stock | Fan-Powered-Unit Filters - One Spare Filter For Each Filter | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 23 36 00_Air Terminal Units | 75
76 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 1.9 | O&M Data | For Air Terminal Units | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 36 00_Air Terminal Units | 76
77 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 1.1 | Warranty - Manufacturer | For Air Terminal Units | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 23 36 00_Air Terminal Units | 77
78 | 23 - Heating, Ventilating, And Air Conditioning (HVAC) | 23 36 00 | Air Terminal Units | 3.7 | Owner Training | Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Air Terminal Units | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 23 36 00_Air Terminal Units | 78
79 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 74 13 | Packaged Rooftop Ventilation Unit | 1.5/C | O&M Data | Operation, And Maintenance Manuals | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 74 13_Packaged Rooftop Ventilation Unit | 79
80 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 74 13 | Packaged Rooftop Ventilation Unit | 1.5/D | Warranty - Sample/Special | 1. Full Parts And Labor Warranty - Atleast 1 Year 2. Compressors - 5 Years | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Sample/Special |  | 23 74 13_Packaged Rooftop Ventilation Unit | 80
81 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.8/B/1 | Attic Stock | Filters - One Set(S) Of Filters For Each Indoor Cooling Unit | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 23 81 25_Refrigerant Based Precision Cooling System | 81
82 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.9 | As-Builts | For Refrigerant Based Precision Cooling System | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | As-Builts |  | 23 81 25_Refrigerant Based Precision Cooling System | 82
83 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.1 | O&M Data | Of Refrigerant Based Precision Cooling System | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 81 25_Refrigerant Based Precision Cooling System | 83
84 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 81 25 | Refrigerant Based Precision Cooling System | 1.11 | Warranty - Contractor | For Refrigerant Based Precision Cooling System | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Contractor |  | 23 81 25_Refrigerant Based Precision Cooling System | 84
85 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 1.7 | Attic Stock | Of Humidifiers | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 23 84 13_Humidifiers | 85
86 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 1.9 | O&M Data | Of Humidifiers | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 23 84 13_Humidifiers | 86
87 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 1.1 | Warranty - Contractor | Of Humidifiers | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Warranty - Contractor |  | 23 84 13_Humidifiers | 87
88 | 23 - Heating, Ventilation, And Air Conditioning (HVAC) | 23 84 13 | Humidifiers | 3.5 | Owner Training | Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Humidifiers. | DLR L236 | Pro Air | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 23 84 13_Humidifiers | 88
89 | 26 - Electrical | 26 00 10 | Basic Electrical Requirements | 1.7 | Attic Stock | Extra Materials For Products Mentioned | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 00 10_Basic Electrical Requirements | 89
90 | 26 - Electrical | 26 00 10 | Basic Electrical Requirements | 1.9 | O&M Data | Provide Operating Instructions And Maintenance Data | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 00 10_Basic Electrical Requirements | 90
91 | 26 - Electrical | 26 00 10 | Basic Electrical Requirements | 1.1 | Warranty - Manufacturer | Manufacturers Shall Provide Their Standard Warranties For Material And Equipment Furnished | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 00 10_Basic Electrical Requirements | 91
92 | 26 - Electrical | 26 05 00 | Common Work Results For Electrical | 1.9 | Attic Stock | Extra Materials For Products Mentioned | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 00_Common Work Results For Electrical | 92
93 | 26 - Electrical | 26 05 00 | Common Work Results For Electrical | 1.9 | O&M Data | Provide All The Required Operation And Maintenance Data | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 00_Common Work Results For Electrical | 93
94 | 26 - Electrical | 26 05 00 | Common Work Results For Electrical | 1.1 | Warranty - Manufacturer | Warranty Must Be Provided For All The Common Work Results For Electrical | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 00_Common Work Results For Electrical | 94
95 | 26 - Electrical | 26 05 19 | Electrical Power Conductors And Cables (600 Volts Or Less) | 1.7 | Attic Stock | Of Electrical Power Conductors And Cables | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 19_Electrical Power Conductors And Cables (600 Volts Or Less) | 95
96 | 26 - Electrical | 26 05 19 | Electrical Power Conductors And Cables (600 Volts Or Less) | 1.9 | O&M Data | Of Electrical Power Conductors And Cables | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 19_Electrical Power Conductors And Cables (600 Volts Or Less) | 96
97 | 26 - Electrical | 26 05 19 | Electrical Power Conductors And Cables (600 Volts Or Less) | 1.1 | Warranty - Manufacturer | For Electrical Power Conductors And Cables | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 19_Electrical Power Conductors And Cables (600 Volts Or Less) | 97
98 | 26 - Electrical | 26 05 26 | Grounding | 1.7 | Attic Stock | Provide Extra Materials For Grounding | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 26_Grounding | 98
99 | 26 - Electrical | 26 05 26 | Grounding | 1.8 | Test-Reports | Reports Of Service Ground Resistance And Resistance Readings From Ground Bar To Ground Bar And From Srg To Raised Floor | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 05 26_Grounding | 99
100 | 26 - Electrical | 26 05 26 | Grounding | 1.8 | O&M Data | Of Grounding | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 26_Grounding | 100
101 | 26 - Electrical | 26 05 26 | Grounding | 1.1 | Warranty - Manufacturer | For Grounding | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 26_Grounding | 101
102 | 26 - Electrical | 26 05 29 | Hangers And Supports For Electrical Systems | 1.7 | Attic Stock | Of Hangers And Supports For Electrcial Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 29_Hangers And Supports For Electrical Systems | 102
103 | 26 - Electrical | 26 05 29 | Hangers And Supports For Electrical Systems | 1.9 | O&M Data | Of Hangers And Supports For Electrcial Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 29_Hangers And Supports For Electrical Systems | 103
104 | 26 - Electrical | 26 05 29 | Hangers And Supports For Electrical Systems | 1.1 | Warranty - Manufacturer | For Hangers And Supports For Electrcial Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 29_Hangers And Supports For Electrical Systems | 104
105 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.7 | Attic Stock | Raceway And Boxes Extra Material For Electrcial Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 33_Raceway And Boxes For Electrical Systems | 105
106 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.8/B/1 | As-Builts | Accurately Record With Dimensions On As-Built Drawings The Locations Of All Concealed Raceways | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | As-Builts |  | 26 05 33_Raceway And Boxes For Electrical Systems | 106
107 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.9 | O&M Data | Of Raceway And Boxes For Electrcial Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 33_Raceway And Boxes For Electrical Systems | 107
108 | 26 - Electrical | 26 05 33 | Raceway And Boxes For Electrical Systems | 1.1 | Warranty - Manufacturer | Warranty Of Raceway And Boxes For Electrcial Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 33_Raceway And Boxes For Electrical Systems | 108
109 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 1.7 | Attic Stock | Of Cable Trays | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 36_Cable Trays For Electrical Systems | 109
110 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 1.9 | O&M Data | Of Cable Trays | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 36_Cable Trays For Electrical Systems | 110
111 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 1.1 | Warranty - Manufacturer | Of Cable Trays | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 36_Cable Trays For Electrical Systems | 111
112 | 26 - Electrical | 26 05 36 | Cable Trays For Electrical Systems | 3.5/B | Test-Reports | Report Field Quality Control Results In Writing After Installation | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 05 36_Cable Trays For Electrical Systems | 112
113 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 1.9 | Attic Stock | Of Cable Trough | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 37_Cable Trough For Electrical Systems | 113
114 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 1.11 | O&M Data | Of Cable Trough | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 37_Cable Trough For Electrical Systems | 114
115 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 1.12 | Warranty - Manufacturer | Of Cable Trough | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 37_Cable Trough For Electrical Systems | 115
116 | 26 - Electrical | 26 05 37 | Cable Trough For Electrical Systems | 3.5/B | Test-Reports | Report Field Quality Control Results In Writing After Installation | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 05 37_Cable Trough For Electrical Systems | 116
117 | 26 - Electrical | 26 05 38 | Cable Bus For Electrical Systems | 1.7 | Attic Stock | Of Cable Bus | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 38_Cable Bus For Electrical Systems | 117
118 | 26 - Electrical | 26 05 38 | Cable Bus For Electrical Systems | 1.9 | O&M Data | Operation And Maintenance Data For Cable Bus | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 38_Cable Bus For Electrical Systems | 118
119 | 26 - Electrical | 26 05 38 | Cable Bus For Electrical Systems | 1.1 | Warranty - Manufacturer | Of Cable Bus | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 38_Cable Bus For Electrical Systems | 119
120 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.6/M | Test-Reports | Source Quality-Control Test Reports | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems | 120
121 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.7/A | Attic Stock | Underground Ducts And Raceways For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems | 121
122 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.8/B | As-Builts | As-Built Drawings | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | As-Builts |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems | 122
123 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.9 | O&M Data | Underground Ducts And Raceways For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems | 123
124 | 26 - Electrical | 26 05 43 | Underground Ducts And Raceways For Electrical Systems | 1.10 | Warranty - Manufacturer | Underground Ducts And Raceways For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 43_Underground Ducts And Raceways For Electrical Systems | 124
125 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.6/I | Test-Reports | Field Quality-Control Test Reports | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 05 48_Vibration And Seismic Controls For Electrical Systems | 125
126 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.7 | Attic Stock | Vibration And Seismic Controls For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 48_Vibration And Seismic Controls For Electrical Systems | 126
127 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.9 | O&M Data | Vibration And Seismic Controls For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 48_Vibration And Seismic Controls For Electrical Systems | 127
128 | 26 - Electrical | 26 05 48 | Vibration And Seismic Controls For Electrical Systems | 1.10 | Warranty - Manufacturer | Vibration And Seismic Controls For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 48_Vibration And Seismic Controls For Electrical Systems | 128
129 | 26 - Electrical | 26 05 53 | Identification For Electrical Systems | 1.7 | Attic Stock | Identification For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 05 53_Identification For Electrical Systems | 129
130 | 26 - Electrical | 26 05 53 | Identification For Electrical Systems | 1.9 | O&M Data | Identification For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 05 53_Identification For Electrical Systems | 130
131 | 26 - Electrical | 26 05 53 | Identification For Electrical Systems | 1.10 | Warranty - Manufacturer | Identification For Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 05 53_Identification For Electrical Systems | 131
132 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 1.7 | Attic Stock | Testing Of Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 08 13_Testing Of Electrical Systems | 132
133 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 1.9 | O&M Data | Testing Of Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 08 13_Testing Of Electrical Systems | 133
134 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 1.10 | Warranty - Manufacturer | Testing Of Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 08 13_Testing Of Electrical Systems | 134
135 | 26 - Electrical | 26 08 13 | Testing Of Electrical Systems | 3.13 | Test-Reports | Electrical Systems | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 08 13_Testing Of Electrical Systems | 135
136 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 1.7 | Attic Stock | Lighting Control Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 09 23_Lighting Control Devices | 136
137 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 1.9 | O&M Data | Lighting Control Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 09 23_Lighting Control Devices | 137
138 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 1.10 | Warranty - Manufacturer | Lighting Control Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 09 23_Lighting Control Devices | 138
139 | 26 - Electrical | 26 09 23 | Lighting Control Devices | 3.7/B | Owner Training | Train Owner'S Maintenance Personnel | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 26 09 23_Lighting Control Devices | 139
140 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.6/D | Test-Reports | Low-Voltage Transformers | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 22 00_Low-Voltage Transformers | 140
141 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.7 | Attic Stock | Low-Voltage Transformers | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 22 00_Low-Voltage Transformers | 141
142 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.9 | O&M Data | Low-Voltage Transformers | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 22 00_Low-Voltage Transformers | 142
143 | 26 - Electrical | 26 22 00 | Low-Voltage Transformers | 1.10 | Warranty - Manufacturer | Low-Voltage Transformers | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 22 00_Low-Voltage Transformers | 143
144 | 26 - Electrical | 26 24 13i | Switchboards - Install | 1.7 | Attic Stock | Switchboards - Install | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 24 13i _Switchboards - Install | 144
145 | 26 - Electrical | 26 24 13i | Switchboards - Install | 1.9 | O&M Data | Switchboards - Install | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 24 13i _Switchboards - Install | 145
146 | 26 - Electrical | 26 24 13i | Switchboards - Install | 1.10 | Warranty - Manufacturer | Switchboards - Install | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 24 13i _Switchboards - Install | 146
147 | 26 - Electrical | 26 24 13i | Switchboards - Install | 3.5 | Test-Reports | Field Quality Control | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 24 13i _Switchboards - Install | 147
148 | 26 - Electrical | 26 24 13i | Switchboards - Install | 3.8/A | Owner Training | Train Owner'S Maintenance Personnel | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 26 24 13i _Switchboards - Install | 148
149 | 26 - Electrical | 26 24 16 | Panelboards | 1.7 | Attic Stock | 1. 6 Of Each Panelboard Key 2. 2 Spare Circuit Breaker Lock-On Devices For Each Panelboard 3. Three Spare Circuit Breakers For Each Size And Type | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 24 16_Panelboards | 149
150 | 26 - Electrical | 26 24 16 | Panelboards | 1.9/B | O&M Data | Maintenance Data | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 24 16_Panelboards | 150
151 | 26 - Electrical | 26 24 16 | Panelboards | 1.10 | Warranty - Manufacturer | Panelboards | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 24 16_Panelboards | 151
152 | 26 - Electrical | 26 24 16 | Panelboards | 3.4 | Test-Reports | Field Quality Control | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 24 16_Panelboards | 152
153 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 1.7 | Attic Stock | Of Power Distribution Units | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 26 00i_Power Distribution Units - Install | 153
154 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 1.9 | O&M Data | Of Power Distribution Units | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 26 00i_Power Distribution Units - Install | 154
155 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 1.1 | Warranty - Manufacturer | Of Power Distribution Units | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 26 00i_Power Distribution Units - Install | 155
156 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 3.5/C | Test-Reports | Submit Documentation Of Tests And Inspections, Along With Manufacturers' Written Instructions And Other Test And Inspection Criteria | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 26 00i_Power Distribution Units - Install | 156
157 | 26 - Electrical | 26 26 00i | Power Distribution Units - Install | 3.9 | Owner Training | Assist Factory-Authorized Service Representative To Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Power Distribution Units | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 26 26 00i_Power Distribution Units - Install | 157
158 | 26 - Electrical | 26 27 26 | Wiring Devices | 1.7 | Attic Stock | Of Wiring Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 27 26_Wiring Devices | 158
159 | 26 - Electrical | 26 27 26 | Wiring Devices | 1.9 | O&M Data | Of Wiring Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 27 26_Wiring Devices | 159
160 | 26 - Electrical | 26 27 26 | Wiring Devices | 1.1 | Warranty - Manufacturer | Of Wiring Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 27 26_Wiring Devices | 160
161 | 26 - Electrical | 26 27 26 | Wiring Devices | 3.4 | Test-Reports | Field Quality Control Tests And Inspection Reports | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 27 26_Wiring Devices | 161
162 | 26 - Electrical | 26 28 13 | Fuses | 1.7 | Attic Stock | 1. 600 Ampere And Smaller: 10 Percent Of Each Rating (Minimum Of 3 Per Rating) 2. 601 Ampere And Larger: 3 Of Each Rating 3. Fuse Pullers: Provide 2 Of Each Type Required 4. Spare Fuse Cabinets | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 28 13_Fuses | 162
163 | 26 - Electrical | 26 28 13 | Fuses | 1.8/B | As-Builts | Record On Final Drawings Actual Fuse Sizes And Types Installed, Adjacent To Each Device | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | As-Builts |  | 26 28 13_Fuses | 163
164 | 26 - Electrical | 26 28 13 | Fuses | 1.9 | O&M Data | Of Fuses | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 28 13_Fuses | 164
165 | 26 - Electrical | 26 28 13 | Fuses | 1.1 | Warranty - Manufacturer | Of Fuses | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 28 13_Fuses | 165
166 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 1.7/B | Attic Stock | A. Spares: 10% Of Installed With A Minimum Of 3 Per Size, For The Following: 1) Control-Power Fuses 2) Fuses For Fused Switches 3) Fuses For Fused Power-Circuit Devices B. Spare Indicating Lights: Six Of Each Type Installed | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 28 16_Enclosed Switches And Circuit Breakers | 166
167 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 1.9 | O&M Data | Of Enclosed Switches And Circuit Breakers | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 28 16_Enclosed Switches And Circuit Breakers | 167
168 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 1.1 | Warranty - Manufacturer | Of Enclosed Switches And Circuit Breakers | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 28 16_Enclosed Switches And Circuit Breakers | 168
169 | 26 - Electrical | 26 28 16 | Enclosed Switches And Circuit Breakers | 3.5/G | Test-Reports | Field Quality Control Tests And Inspection Reports Including A Certified Report That Identifies Enclosed Switches And Circuit Breakers | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 28 16_Enclosed Switches And Circuit Breakers | 169
170 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.6/B | Test-Reports | Written Test Results | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 32 13i_Engine Generators - Install | 170
171 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.7/B | Attic Stock | 1. One Spare Set Of Consumables Such As Fuses, Filters, Etc. 2. One Spare Set Of Air, Fuel And Oil Filters In Addition To Those To Be Installed After Acceptance And Integrated Systems Testing | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 32 13i_Engine Generators - Install | 171
172 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.9 | O&M Data | Of Engine Generators | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 32 13i_Engine Generators - Install | 172
173 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 1.1 | Warranty - Manufacturer | Of Engine Generators | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 32 13i_Engine Generators - Install | 173
174 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 3.5/A | Test-Reports | Field Quality Control Tests And Inspection Reports | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 32 13i_Engine Generators - Install | 174
175 | 26 - Electrical | 26 32 13i | Engine Generators - Install | 3.6/A | Owner Training | Assist Factory-Authorized Service Representative To Train Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Packaged Engine Generators | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 26 32 13i_Engine Generators - Install | 175
176 | 26 - Electrical | 26 32 15 | Engine Generator Field Startup Requirements | 1.7 | Attic Stock | 1. One Spare Set Of Consumables Such As Fuses, Filters, Etc. 2. One Spare Set Of Air, Fuel And Oil Filters In Addition To Those To Be Installed After Acceptance And Integrated Systems Testing | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 32 15_Engine Generator Field Startup Requirements | 176
177 | 26 - Electrical | 26 32 15 | Engine Generator Field Startup Requirements | 3.4/A | Test-Reports | Oil Analysis Written Report | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 26 32 15_Engine Generator Field Startup Requirements | 177
178 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 1.7 | Attic Stock | Static Uninterruptible Power Supply - Install | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 33 53i_Static Uninterruptible Power Supply - Install | 178
179 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 1.9 | O&M Data | Static Uninterruptible Power Supply - Install | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 33 53i_Static Uninterruptible Power Supply - Install | 179
180 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 33 53i_Static Uninterruptible Power Supply - Install | 180
181 | 26 - Electrical | 26 33 53i | Static Uninterruptible Power Supply - Install | 3.9/A | Owner Training | Train Owner'S Maintenance Personnel | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 26 33 53i_Static Uninterruptible Power Supply - Install | 181
182 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.6/E | Attic Stock | Field Quality-Control Reports | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 41 13_Lightning Protection For Structures | 182
183 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.7 | Attic Stock | Lightning Protection For Structures | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 41 13_Lightning Protection For Structures | 183
184 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.8/B | As-Builts | As-Built Drawings | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | As-Builts |  | 26 41 13_Lightning Protection For Structures | 184
185 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.9 | O&M Data | Lightning Protection For Structures | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 41 13_Lightning Protection For Structures | 185
186 | 26 - Electrical | 26 41 13 | Lightning Protection For Structures | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 41 13_Lightning Protection For Structures | 186
187 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 1.7 | Attic Stock | One Set Of Spare Fuses Of Each Type Used | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 43 13_Surge Protective Devices | 187
188 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 1.9 | O&M Data | Surge Protective Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 43 13_Surge Protective Devices | 188
189 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 1.10/A | Warranty - Manufacturer | Surge Protective Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 43 13_Surge Protective Devices | 189
190 | 26 - Electrical | 26 43 13 | Surge Protective Devices | 3.5/A | Owner Training | Train Owner'S Maintenance Personnel To Maintain Spd Devices | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 26 43 13_Surge Protective Devices | 190
191 | 26 - Electrical | 26 51 00 | Lighting | 1.7 | Attic Stock | 1. Provide Two Of Each Plastic Lens 2. Provide One Case (Minimum Of 12) Replacement Lamps For Each Type Of Lamp And Wattage Installed. Provide Five Cases (60 Lamps) Of Four-Foot Fluorescent Lamps 3. Provide Two Of Each Ballast Type And Rating 4. Provide Spare Fuses For Fused Fixtures Equal To 10% Of Total Installed Of Each Type | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 26 51 00_Lighting | 191
192 | 26 - Electrical | 26 51 00 | Lighting | 1.9 | O&M Data | Lighting | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 26 51 00_Lighting | 192
193 | 26 - Electrical | 26 51 00 | Lighting | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 26 51 00_Lighting | 193
194 | 26 - Electrical | 26 51 00 | Lighting | 3.7/B | Owner Training | Demonstration Of Luminaire Operation - 2 Hours | DLR L236 | Power Solutions | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 26 51 00_Lighting | 194
195 | 27 - Communications | 27 05 26 | Grounding And Bonding For Communications Systems | 1.7 | Attic Stock | Grounding And Bonding For Communications Systems | DLR L236 | TBD | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 27 05 26_Grounding And Bonding For Communications Systems | 195
196 | 27 - Communications | 27 05 26 | Grounding And Bonding For Communications Systems | 1.9 | O&M Data | Grounding And Bonding For Communications Systems | DLR L236 | TBD | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 27 05 26_Grounding And Bonding For Communications Systems | 196
197 | 27 - Communications | 27 05 26 | Grounding And Bonding For Communications Systems | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | TBD | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 27 05 26_Grounding And Bonding For Communications Systems | 197
198 | 27 - Communications | 27 05 28 | Low Voltage Raceway Systems | 1.7 | Attic Stock | Low Voltage Raceway Systems | DLR L236 | TBD | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 27 05 28_Low Voltage Raceway Systems | 198
199 | 27 - Communications | 27 05 28 | Low Voltage Raceway Systems | 1.9 | O&M Data | Low Voltage Raceway Systems | DLR L236 | TBD | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 27 05 28_Low Voltage Raceway Systems | 199
200 | 28 - Electronic Safety And Security | 28 08 00 | Security Systems Commissioning | 1.04/2 | O&M Data | Security Systems Commissioning | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 28 08 00_Security Systems Commissioning | 200
201 | 28 - Electronic Safety And Security | 28 08 00 | Security Systems Commissioning | 3.04/A | As-Builts | Detailed Wiring Diagram | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | As-Builts |  | 28 08 00_Security Systems Commissioning | 201
202 | 28 - Electronic Safety And Security | 28 08 00 | Security Systems Commissioning | 3.05/A | Owner Training | Owner Instruction In The Operation And Testing Of The System | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 28 08 00_Security Systems Commissioning | 202
203 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.6/D | Test-Reports | Satisfactory Completion Of Required Tests And Inspections | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | Test-Reports |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD | 203
204 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.7 | Attic Stock | 1. Ten Manual Station Break-Glass Rods 2. Six Keys Of Each Type 3. Three Of Each Type Of Automatic Smoke Detector | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | Attic Stock |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD | 204
205 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.9 | O&M Data | Digital, Addressable Fire-Alarm System - Tkd | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | O&M Data |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD | 205
206 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 1.10 | Warranty - Manufacturer | Warranty | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | Warranty - Manufacturer |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD | 206
207 | 28 - Electronic Safety And Security | 28 31 12 | Digital, Addressable Fire-Alarm System - TKD | 3.7/A | Owner Training | Rain Owner'S Maintenance Personnel To Adjust, Operate, And Maintain Fire-Alarm System | DLR L236 | AVS Technology | 0 | 0 | 0 |  |  | 1 | Owner Training |  | 28 31 12_Digital, Addressable Fire-Alarm System - TKD | 207
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 208
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 209
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 210
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 211
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 212
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 213
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 214
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 215
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 216
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 217
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 218
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 219
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 220
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 221
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 222
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 223
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 224
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 225
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 226
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 227
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 228
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 229
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 230
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 231
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 232
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 233
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 234
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 235
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 236
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 237
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 238
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 239
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 240
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 241
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 242
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 243
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 244
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 245
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 246
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 247
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 248
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 249
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 250
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 251
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 252
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 253
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 254
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 255
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 256
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 257
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 258
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 259
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 260
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 261
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 262
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 263
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 264
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 265
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 266
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 267
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 268
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 269
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 270
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 271
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 272
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 273
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 274
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 275
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 276
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 277
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 278
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 279
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 280
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 281
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 282
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 283
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 284
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 285
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 286
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 287
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 288
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 289
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 290
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 291
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 292
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 293
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 294
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 295
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 296
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 297
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 298
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 299
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 300
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 301
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 302
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 303
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 304
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 305
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 306
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 307
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 308
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 309
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 310
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 311
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 312
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 313
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 314
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 315
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 316
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 317
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 318
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 319
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 320
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 321
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 322
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 323
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 324
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 325
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 326
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 327
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 328
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 329
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 330
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 331
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 332
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 333
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 334
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 335
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 336
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 337
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 338
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 339
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 340
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 341
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 342
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 343
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 344
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 345
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 346
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 347
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 348
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 349
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 350
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 351
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 352
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 353
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 354
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 355
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 356
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 357
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 358
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 359
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 360
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 361
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 362
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 363
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 364
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 365
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 366
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 367
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 368
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 369
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 370
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 371
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 372
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 373
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 374
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 375
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 376
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 377
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 378
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 379
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 380
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 381
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 382
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 383
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 384
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 385
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 386
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 387
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 388
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 389
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 390
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 391
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 392
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 393
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 394
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 395
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 396
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 397
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 398
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 399
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 400
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 401
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 402
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 403
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 404
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 405
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 406
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 407
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 408
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 409
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 410
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 411
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 412
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 413
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 414
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 415
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 416
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 417
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 418
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 419
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 420
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 421
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 422
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 423
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 424
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 425
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 426
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 427
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 428
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 429
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 430
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 431
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 432
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 433
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 434
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 435
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 436
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 437
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 438
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 439
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 440
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 441
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 442
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 443
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 444
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 445
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 446
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 447
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 448
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 449
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 450
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 451
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 452
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 453
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 454
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 455
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 456
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 457
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 458
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 459
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 460
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 461
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 462
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 463
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 464
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 465
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 466
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 467
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 468
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 469
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 470
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 471
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 472
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 473
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 474
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 475
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 476
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 477
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 478
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 479
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 480
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 481
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 482
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 483
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 484
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 485
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 486
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 487
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 488
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 489
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 490
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 491
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 492
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 493
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 494
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 495
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 496
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 497
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 498
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 499
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 500
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 501
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 502
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 503
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 504
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 505
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 506
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 507
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 508
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 509
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 510
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 511
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 512
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 513
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 514
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 515
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 516
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 517
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 518
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 519
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 520
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 521
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 522
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 523
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 524
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 525
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 526
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 527
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 528
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 529
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 530
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 531
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 532
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 533
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 534
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 535
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 536
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 537
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 538
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 539
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 540
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 541
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 542
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 543
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 544
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 545
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 546
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 547
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 548
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 549
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 550
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 551
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 552
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 553
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 554
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 555
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 556
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 557
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 558
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 559
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 560
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 561
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 562
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 563
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 564
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 565
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 566
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 567
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 568
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 569
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 570
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 571
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 572
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 573
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 574
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 575
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 576
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 577
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 578
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 579
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 580
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 581
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 582
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 583
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 584
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 585
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 586
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 587
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 588
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 589
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 590
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 591
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 592
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 593
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 594
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 595
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 596
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 597
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 598
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 599
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 600
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 601
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 602
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 603
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 604
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 605
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 606
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 607
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 608
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 609
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 610
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 611
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 612
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 613
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 614
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 615
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 616
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 617
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 618
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 619
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 620
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 621
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 622
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 623
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 624
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 625
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 626
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 627
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 628
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 629
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 630
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 631
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 632
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 633
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 634
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 635
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 636
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 637
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 638
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 639
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 640
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 641
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 642
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 643
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 644
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 645
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 646
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 647
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 648
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 649
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 650
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 651
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 652
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 653
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 654
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 655
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 656
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 657
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 658
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 659
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 660
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 661
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 662
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 663
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 664
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 665
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 666
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 667
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 668
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 669
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 670
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 671
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 672
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 673
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 674
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 675
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 676
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 677
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 678
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 679
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 680
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 681
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 682
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 683
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 684
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 685
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 686
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 687
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 688
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 689
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 690
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 691
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 692
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 693
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 694
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 695
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 696
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 697
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 698
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 |  | 0_0 | 699

## Review sheet (hidden)
Sr. No | Subcontractor | Closeout Document |  | Total# to be received | Received# | Blocks/Buildings | Closeout Document | Total# to be received | Received# | Helper
1 |  | Mockups | Mockups | 1 | 0 | DLR L236 | Mockups | 1 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Yes
2 |  | O&M Data | O&M Data | 47 | 0 | DLR L242 | O&M Data | 47 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | No
3 |  | Warranty | Warranty | 0 | 0 | Common | Warranty | 59 | 0
4 |  | Warranty - Installer | Warranty | 1 | 0 | DH F | Test-Reports | 29 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 |  | Warranty - Manufacturer | Warranty | 51 | 0 | Common | Owner Training | 16 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | Warranty - Contractor | Warranty | 3 | 0 | Name 5 | Attic Stock | 43 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 |  | Warranty - Sample/Special | Warranty | 4 | 0 |  | Keys | 1 | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
8 |  | Test-Reports | Test-Reports | 29 | 0 |  | As-Builts | 7 | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
9 |  | Owner Training | Owner Training | 16 | 0 |  | Other | 4 | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
10 |  | Attic Stock | Attic Stock | 43 | 0 | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
11 |  | Keys | Keys | 1 | 0 | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
12 |  | As-Builts | As-Builts | 7 | 0 | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
13 |  | Other | Other | 4 | 0 | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
14 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
15 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
16 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
17 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
18 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
19 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
20 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
21 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
0
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Sheet2 (hidden)
YES
NO
VOID
TBD